Time table 2017:

|  |  |  |  |
| --- | --- | --- | --- |
| **Month of 2017** | **Activity** | **Organisation(s)** | **Output** |
| Jan-Apr. | Various follow-up to the Dec. 2016 workshop, inc. preparation of minutes from meetings, and several media releases | APN, SnowChange, NORDECO | Minutes, media releases |
| May | Publication on traditional knowledge and food by Sustainable Development Working Group, at the Week of the Arctic  | ICRH | Book, event |
| May | Participation in panel discussion, indigenous and local knowledge for decision-making, International Arctic Assembly | NORDECO | Video (streamed) |
| May-August | Continued pilot testing of templates Arsuk and Nanortalik, Greenland, and training of the local Natural Resource Councils | APN, GINR, NORDECO | Technical report, minutes |
| June 2017 | Steering Committee Meeting | Members of the Project Steering Committee | Minutes |
| Nov. 2017 | Completion of ”Ungulate Calculator”, a software for hunters/biologists to project consequences of management decisions  | GINR, APN | Software w. instructions and examples  |
| To be determined | Preparation of policy brief for Nordic Council of Ministers | All  | Policy Brief |
| To be determined | Training webinar | To be determined | One-page intro manual drafted by participants |
| Dec. 2017 | Project report  | All | Report |